## Slide 1: Report on BILC Shared Item Bank Project
Shared Item Bank Working Group
Merit Kompus, Estonian Military Academy
BILC Testing Workhsop, September 2022

## Slide 2: BILC Shared Item Bank Project
The project was launched in February 2020
Working group members:
Canada Nancy Powers, May Tan
Croatia Suzana Horvat, Tamara Kramaric, Kristina Serdoz
Estonia Merit Kompus, Marju Laurits
Latvia Inga Farte–Zalite, Julija Kolosovska
Romania Corina Ispas, Andreea Marinescu
Slovakia Maria Vargova, Gabriela Repova
Slovenia Tadeja Hafner

## Slide 3: Project Goals
create a bank of reading and listening anchor items for Levels 1, 2 and 3
ensure that all nations using the STANAG 6001 Language Proficiency scale are normed in their interpretation and application of the standard, and that their items and tests are at the intended STANAG level
help testing organizations in establishing their nations’ best test development and item moderation practices
strengthen linguistic interoperability among NATO and Partner nations by furthering standardization of language testing

## Slide 4: What have we done so far?
In 2020
Created item specifications for reading
Designed and submitted 47 items (L1 – 12 items, L2 – 17 items, L3 – 18 items)
Revised and moderated items in national teams
Worked on online multinational item moderation procedures

## Slide 5: What have we done so far?
2021 - August 2022
Held 14 online item moderation sessions
Retained 43 items (L1 - 11 items, L2 - 15 items, L3 - 17 items)
Piloted items on 21 teachers from Canada, Latvia, Romania and Slovakia
Kept in total 42 items for pre-testing and compiled two pre-test versions
Devised a plan for pre-testing

## Slide 6: Next steps
large scale pre-testing of reading items
quantitative and qualitative analysis of reading items
final revision and setting up the item bank for reading items
repeating the procedure for listening items

## Slide 7: Until now…

## Slide 8: Now…

## Slide 9: Request for help: pre-testing of reading items
Two multilevel reading tests, each consisting of 24 MCQ items
Paper-and-pencil test
Test length 90 minutes
Volunteers with a wide range of ability, at least 30 people per country
ALCPT/STANAG results
Pre-testing period from October to December 15
Feedback to test takers

## Slide 10: Shared Item Bank POCs for pre-testing
Ms May Tan may.tan@forces.gc.ca
Ms Suzana Horvat suzana.horvat.ce@gmail.com
THANK YOU!