## Slide 1: Report on the BILC Shared Item Bank Project Merit Kompus, Estonian Military Academy BILC Steering Commitee Meeting, May 2023
Working group members:
Canada Nancy Powers, May Tan
Croatia Suzana Horvat, Tamara Kramaric, Kristina Serdoz
Estonia Merit Kompus, Marju Laurits
Latvia Inga Farte–Zalite, Julija Kolosovska
Romania Corina Ispas, Andreea Marinescu
Slovakia Maria Vargova, Gabriela Repova
Slovenia Tadeja Hafner
Project goal:
Create a bank of reading and listening anchor items for Levels 1, 2 and 3

## Slide 2: Reading item development
Designed 47 items (L1 – 12 items, L2 – 17 items, L3 – 18 items)
Revised and moderated items in national teams
Held 14 online item moderation sessions
Piloted items on teachers from Canada, Latvia, Romania and Slovakia
Kept 42 items for pre-testing and compiled two pre-test versions
Asked nations for volunteers for pre-testing

## Slide 3
Pre-testing from October to December 2022
Volunteers from 16 countries:
Austria, Belgium, Bosnia and Herzegovina, Bulgaria, Croatia, Estonia, Georgia, Italy, Latvia, Lithuania, Montenegro, North Macedonia, Poland, Portugal, Romania, Spain
Version 1 N=515
Version 2 N=497
THANK YOU!

## Slide 4: Statistical analysis & results
Programmes used: TiaPlus for CTT and jMetric, jamovi, gui Dexter module in RStudio for Rasch analysis, Wright Map module in Rstudio
Retained:
L1 – 4 items
L2 – 3 items
L3 – 7 items
The report and the items will be available after the Testing Workshop in Riga

## Slide 5
Work-in-progress and next steps
Created item specifications for listening
Designed and submitted 45 listening items (L1 – 15 items, L2 – 15 items, L3 – 15 items)
Revised and moderated L1 and L2 items in national teams
Held two online item moderation sessions
Large scale pre-testing of listening items in 2024
Analysis and setting up the item bank of listening items
Inviting other nations to join the project