## Slide 1
SHARED
ITEM
BANK
Suzana HORVAT
SIB Working Group
2025 NATO BILC Conference
Zagreb, Croatia
PROJECT STATUS

## Slide 2: Introduction and Background
Origin of the idea – 2019 Testing Workshop in Tours
Launch of the SIB Working Group - 2020
Initially 7 countries → currently 6
Canada Croatia Estonia
Latvia Romania Slovenia
Collaborative approach: online meetings, shared platforms

## Slide 3: Project Goals
Develop reading and listening anchor items (Levels 1-3)
Build a Shared Item Bank for calibration and benchmarking
Ensure standardization in STANAG 6001 interpretation
Improve score comparability across nations

## Slide 4: Methodology
Work phases:
  Reading anchor items (Levels 1-3)
  Listening anchor items (Levels 1-3)
Item format: MCQ
Item development:
  text selection and item creation in national teams
  peer review online
  Working Group online moderation sessions
Platforms used: MS Teams, Google Drive, Zoom

## Slide 5: Reading Anchor Item Phase (2020-2022)
47 reading items developed and finalized
Pretested on 1,000 candidates from 16 countries
Two test versions
Classical and IRT analysis (TiaPlus, Jamovi, jMetrik)
Selection based on facility and discrimination indices
Outcome: 14 validated anchor items
(4 L1, 3 L2, 7 L3)

## Slide 6: Distribution
Non-disclosure agreement + Guidelines for Use
Distribution only to countries with STANAG testing in place
18 countries currently using anchor items
Feedback required after one year

## Slide 7: Support materials
Reading sample items on BILC website / Testing Resources
  Serve as models for other nations’ item writers
Guidelines for the Use of Anchor Items
BILC SIB Report on the Development of Items
Statistical Techniques & Analysis for Testers Seminar (STATS)

## Slide 8: Listening Anchor Item Phase (2023-2025)
82 items developed; 59 retained after moderation
Two test versions with common items for comparison
Small-scale pilot on teachers and colleagues (May 2025)
Full pretesting (Sep-Dec 2025)

## Slide 9: Listening item challenges
Higher logistical requirements
  Audio labs, special equipment, standardized conditions
  Limited number of seats in labs or testing rooms

## Slide 10: After pre-testing
Statistical analyses
Selection of best-performing listening anchor items
Distribution process - the same as in reading item phase

## Slide 11: Future plans
Open the Working Group to new nations
Continuous development of anchor items
Improve standardization and test-score comparability
Encourage broader collaboration and sharing of best practices
Strengthen national testing expertise and resources

## Slide 12: Support and Engagement
Inviting nations to support listening pretesting
Encouraging the use of reading anchor items
Promote feedback and data sharing for mutual benefit

## Slide 13
Thank you !