## Slide 1
BILC SHARED ITEM BANK
Progress Update
NATO BILC Testing Workshop
Sarajevo 2026
Merit Kompus
Shared Item Bank WG

## Slide 2
Canada
Croatia
Estonia
Latvia
Romania
Slovenia
This is Us

## Slide 3
  Project launched in 2020 with seven nations
  Online collaboration,development and moderation
  2020–2021: Foundations and test specifications
  2024: Reading phase completed
  2026: Listening phase completed
Project Overview

## Slide 4
  Develop reading & listening anchor items for STANAG 6001 Levels 1–3
  Support a common interpretation and application of the STANAG 6001 scale
  Promote best testing practices
  Strengthen NATO linguistic interoperability
Project Goals

## Slide 5
  42 items pretested with 1,000 candidates from 16 countries
  14 reading anchor items released in 2024
  Guidelines on the Use of Anchor Items
  Development report distributed
  6 sample items published on the BILC website
  18 countries requested and received access
  Feedback collected from participating countries
  Other interested countries can still request access
Reading Phase

## Slide 6
  Two-year development cycle
  18 online moderation sessions
  82 items developed → 59 retained
  Items piloted on 40 teachers → 57 retained
  Items pretested (Oct 2025 – Feb 2026)
  920 candidates from 18 countries
  Statistical analysis completed
  13 anchor items: L1 - 4, L2 - 3, L3 - 6
Listening Phase

## Slide 7
  Release of listening anchor items: September 15
  Distribution of the item development report
  Guidelines on the Use of Anchor Items
  Sample listening items on the BILC website
Following the TW

## Slide 8
sibanchoritems@gmail.com
Suzana Horvat, Merit Kompus, Marju Laurits
Contact Information

## Slide 9
Revising Best Practices in STANAG 6001 Testing by
        building on the SIB experience
        gathering input from the BILC community
        keeping up with developments in language testing
Next Steps